## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | High | 5 | 8 | Use the planned debugging time in the iteration.
2 | 1 | Login (User) | Login page has undefined variable 'error' | Low | 1 |  | Fixed
3 | 1 | Login (User) | Login page displayed error message "A session had already been started" | Low | 1
4 | 1 | Biding | Biding page displayed syntax error, unexpected '}' | Low | 1
5 | 2 | Admin(Bootstrap) | When importing SamplateData(3) zip file to validate section.csv, actual result was correct but it gave warning of ' Undefined variable:field in include/bootstrap.php on line 254' | Low | 1 | 32 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
6 | 2 | Admin(Bootstrap) | When importing a zip file with missing student.csv, actual result was correct but it gave warning of 'invalid argument supplied for foreach() in processBootstrap.php o line89' . | Low | 1
7 | 2 | Admin(Bootstrap) | When importing SamplateData(1) zip file to validate student.csv, actual result was correct but it gave warning of 'Trying to get property edollar of 'non-object' in include/BidDAO.php on line 107' | Low | 1
8 | 2 | Admin(Bootstrap) | Unable to validate exam start and end time in course.csv (exam start time later than end time) | High | 5
9 | 2 | Admin(Bootstrap) | Unable to validate userid with different casing in course_completed.csv | High | 5
10 | 2 | Admin(Bootstrap) | Unable to display error messages when importing SampleData(6 and 7).zip to validate bid.csv | Low | 1
11 | 2 | Bidding (add bid) | Unable to update bid amount when student bid twice for same section in the same round | High | 5
12 | 2 | Bidding (add bid) | Unable to validate if student has not completed the prerequisite | High | 5
13 | 2 | Bidding(add bid) | When validating if student can add a bid with an incorrect course code, page displayed notice of 'Trying to get property 'school' of non-object'. | Low | 1
14 | 2 | Bidding(drop bid) | Unable to drop a bid with correct course code and section number | High | 5
15 | 2 | Bidding(drop section) | After importing r1_solution_test_2 zip file to validate round1 clearing of 2bids at the clearing price, actual result was correct but page displayed 8 bids succeed | Low | 1
16 | 2 | Bidding(drop section) | After importing r1_solution_test_4 zip file to validate round1 clearing of 11bids at the clearing price, actual result was correct but page displayed 10 succeed bids | Low | 1
17 | 3 | Admin(Bootstrap) | After click the button to import SampleData_lter3.zip file. There is a error of array to string conversion | High | 1 | 1 | Use the planned debugging time in the iteration.
High
High
High
|  |  |  | Low |  | 0 | Use the planned debugging time in the iteration.
High
Low

## Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team) | Result1
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | Resolved | 2019-09-24 | 2019-09-30 | MLJX+ SHKX
2 | 1 | Login (User) | Login page has undefined variable 'error' | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
3 | 1 | Login (User) | Login page displayed error message "A session had already been started" | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
4 | 1 | Biding | Biding page displayed syntax error, unexpected '}' | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
5 | 2 | Admin(Bootstrap) | When importing SamplateData(3) zip file to validate section.csv, actual result was correct but it gave warning of ' Undefined variable:field in include/bootstrap.php on line 254' | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
6 | 2 | Admin(Bootstrap) | When importing a zip file with missing student.csv, actual result was correct but it gave warning of 'invalid argument supplied for foreach() in processBootstrap.php o line89' . | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
7 | 2 | Admin(Bootstrap) | When importing SamplateData(1) zip file to validate student.csv, actual result was correct but it gave warning of 'Trying to get property edollar of 'non-object' in include/BidDAO.php on line 107' | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
8 | 2 | Admin(Bootstrap) | Unable to validate exam start and end time in course.csv (exam start time later than end time) | Unresolved | 2019-09-29
9 | 2 | Admin(Bootstrap) | Unable to validate userid with different casing in course_completed.csv | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
10 | 2 | Admin(Bootstrap) | Unable to display error messages when importing SampleData(6 and 7).zip to validate bid.csv | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
11 | 2 | Bidding (add bid) | Unable to update bid amount when student bid twice for same section in the same round | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
12 | 2 | Bidding (add bid) | Unable to validate if student has not completed the prerequisite | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
13 | 2 | Bidding(add bid) | When validating if student can add a bid with an incorrect course code, page displayed notice of 'Trying to get property 'school' of non-object'. | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
14 | 2 | Bidding(drop bid) | Unable to drop a bid with correct course code and section number | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
15 | 2 | Bidding(drop section) | After importing r1_solution_test_2 zip file to validate round1 clearing of 2bids at the clearing price, actual result was correct but page displayed 8 bids succeed | Unresolved
16 | 2 | Bidding(drop section) | After importing r1_solution_test_4 zip file to validate round1 clearing of 11bids at the clearing price, actual result was correct but page displayed 10 succeed bids | Unresolved
0 | 0 | 0 | 0 | Unresolved
0 | 0 | 0 | 0 | Unresolved
0 |  | 0 | 0
0 |  | 0 | 0
0 |  | 0 | 0
0 |  | 0 | 0
0 |  | 0 | 0
0 |  | 0 | 0
0 |  | 0 | 0
0 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0