## Week 7
Person | Question | Week 7: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | added dropSection.php page added retrieveByUserid, retrieveByUseridCourse, delete functions changed alignment formatting and UI added CSS for frontend pages, login.php now retains userid after wrong login | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug
| What will you do today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code
| Do you have any obstacles? | No issues | No issues | no issues
Maurice | What did you do yesterday? | Not a working day | added Validation for drop bid, validation test code for R2 add bid Reorder retrieve and add and Changed DropBid layout | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug
| What will you work on today? | Drop Bid validation, polish up the bidding pages, create Round objects with Zican | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code
| Do you have any obstacles? | No issues | No issues | no issues
Sebastian | What did you do yesterday? | Not a working day | added dropSection.php page added retrieveByUserid, retrieveByUseridCourse, delete functions changed alignment formatting and UI added CSS for frontend pages, login.php now retains userid after wrong login | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug
| What will you work on today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code
| Do you have any obstacles? | No issues | No issues | no issues
Sujuan | What did you do yesterday? | Not a working day | Tested bidding for round 1 and updated bug metrics | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug
| What will you work on today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code
| Do you have any obstacles? | No issues | No issues | no issues
Zican | What did you do yesterday? | Not a working day | added Validation for drop bid, validation test code for R2 add bid Reorder retrieve and add and Changed DropBid layout | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug
| What will you work on today? | Drop Bid validation, polish up the bidding pages, create Round objects with Maurice | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code
| Do you have any obstacles? | No issues | No issues | No issues

## Week 6
| Question | Week 6: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Create testcase for login, add bid and bootstrap | Not a working day | Planned logic for round 1 clearing | Not a working day | Coded round 1 validation logic | Coded round 1 result page and debugging | Not a working day
| What will you do today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Code round 1 result page and debugging | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No Issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Discussed round 1 clearing logic with team | Not a working day | Not a working day | Add bid validation with Zican | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Add bid validation with Zican | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Fix authentication bug for admin | authentication for admin, home & bootstrap page for admin Planned logic for round 1 clearing | Not a working day | Coded round 1 validation logic | Fixed bugs on login page and created Web UI page for round 1 clearing and round 1 result display | Not a working day
| What will you work on today? | Fix authentication bug for admin | authentication for admin, home & bootstrap page for admin Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Code round 1 result page and debugging | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Create Drop Bid function and update bidding functionality | NA | Discussion of round 1 clearing logic and tested bootstrap and login with test cases | Not a working day | Update testcases and documentation for login and bidding function | Create testcases for round 1 bidding and resolution | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Create testcases for round 1 bidding and resolution, prepare PM review power point slides | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Add data validation for course_completed and create test cases | Not a working day | Not a working day | Not a working day | Not a working day | Add bid validation with Maurice | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Add bid validation with Maurice | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | No issues | No issues | No issues | No issues

## Week 5
Person | Question | Week 5: 16 September 2019 to 22 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Created remainder of DAO files from what Maurice did on Saturday, added deleteAll and add method to all DAO files for bootstrap. | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with ZiCan) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed bootstrap
| What will you do today? | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with ZiCan) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed bootstrap | Create testcase for login, add bid and bootstrap
| Do you have any obstacles? | No issues | Problem with data validation for course_completed, prerequisite completed validation | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Round 1 bidding form, session for login, logout with Sebastian | Not a working day | Add new bid, update existing bid functionality with Sujuan | Update and debug existing bid functionality with Sujuan | Not a working day | Add input and logical vaildation for bid section with Sujuan
| What will you work on today? | session for login, logout, added get course by student id. started round 1 bidding form with Sebastian. | Filters for sections to bid with Sujuan | Meeting to discuss schedule Discuss data validation for course_completed and bid table Add new bid, update existing bid functionality with Sujuan | Update and debug existing bid functionality with Sujuan | Not a working day | Add input and logical vaildation for bid section with Sujuan | Not a working day
| Do you have any obstacles? | No issues | Postponed filtering, going to focus on the bidding functionality first. | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Added CSS navigation bar to home page | Round 1 bidding form, session for login, logout with Maurice | Round 1 bidding form | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | added load admin sql, admin class & DAO (add, reset passwod). to finish authenticate & test | Not a working day
| What will you work on today? | session for login, logout, added get course by student id. started round 1 bidding form with Maurice. | Round 1 bidding form | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | added load admin sql, admin class & DAO (add, reset passwod). to finish authenticate & test | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | To debug and test | No issues | No issues
Sujuan | What did you do yesterday? | Add retrieve by course and section methods. | Not a working day | Not a working day | Add new bid, update existing bid functionality with Maurice | Update and debug existing bid functionality with Maurice | Not a working day | Add input and logical vaildation for bid section
| What will you work on today? | Not a working day | Filters for sections to bid with Maurice | Meeting to discuss schedule Discuss data validation for course_completed and bid table Add new bid, update existing bid functionality with Maurice | Update and debug existing bid functionality with Maurice | Not a working day | Add input and logical vaildation for bid section with Maurice | Not a working day
| Do you have any obstacles? | No issues | Postponed filtering, going to focus on the bidding functionality first. | No Issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Created Login page with authentication from database | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with Zheng Yang) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed
| What will you work on today? | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with Zheng Yang) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed | Add data validation for course_completed and create test cases
| Do you have any obstacles? | No issues | Problem with data validation for course_completed, prerequisite completed validation | No issues | No issues | No issues | No issues | No issues

## Week 4
Person | Question | Week 4: 9 September 2019 to 15 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? |  |  |  |  | NA | Team meeting | Created minutes for meeting
| What will you do today? |  |  |  |  | Team meeting | Created minutes for meeting | Created remainder of DAO files from what Maurice did on Saturday, added deleteAll and add method to all DAO files for bootstrap.
| Do you have any obstacles? |  |  |  |  | No issues | No Issues | No issues
Maurice | What did you do yesterday? |  |  |  |  | NA | Change folder structure on repo to the one on wiki Create barebones class files for the 6 DB tables | Create a couple of basic retrieveAll() methods
| What will you work on today? |  |  |  |  | Change folder structure on repo to the one on wiki Create barebones class files for the 6 DB tables Team meeting | Create a couple of basic retrieveAll() methods | Not a working day
| Do you have any obstacles? |  |  |  |  | Had to make placeholder files to push empty folders to github | NA | NA
Sebastian | What did you do yesterday? |  |  |  |  | NA | Team Meeting | Not a working day
| What will you work on today? |  |  |  |  | Team Meeting | Not a working day | Added CSS navigation bar to home page
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | No issues
Sujuan | What did you do yesterday? |  |  |  |  | NA | NA | NA
| What will you work on today? |  |  |  |  | Team meeting | Not a working day | Add retrieve by course and section methods in the course and section DAO. Create Course_completedDAO
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | NA
Zican | What did you do yesterday? |  |  |  |  | NA | Team meeting | Not a working day
| What will you work on today? |  |  |  |  | Team meeting | Not a working day | Created Login page with authentication from database
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | No Issues