## Manual Chart
| TASK NAME | START DATE | END DATE | Hours planned | Actual Start Date / Time | Actual End Date / Time | TEAM MEMBER | PERCENT COMPLETE | Remarks | WEEK 4 (9/9 - 15/9) | [6 empty] | WEEK 5 (16/9 - 22/9) | [6 empty] | WEEK 6 (23/9 - 29/9) | [6 empty] | WEEK 7 (30/9 - 6/10) | [6 empty] | WEEK 8 (7/10 - 13/10) | [6 empty] | WEEK 9 (14/10 - 20/10) | [6 empty] | WEEK 10 (21/10 - 27/10) | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14
[10 empty] | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S | M | T | W | Th | F | S | S
Iteration 1
1 | Read Project Wiki as a Team | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
| 1.1Understand Requirement | 13/09/2019 | 13/09/2019 | 2 |  |  | All | 100% | bar: WEEK 4 (9/9 - 15/9) F; WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2 | Planning & delegation | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
| 2.1 Develop critical path for iteration 1 and 2 | 13/09/2019 | 19/09/2019 | 2 |  |  | All | 20% | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) Th
| 2.2 Work breakdown structure | 13/09/2019 | 19/09/2019 | 1 |  |  | All | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) Th
| 2.3 Delegation of task | 13/09/2019 | 19/09/2019 | 0.5 |  |  | All | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) Th
| 2.4 Begin preparing power point slides for week 7 | 13/09/2019 | 19/09/2019 | 1 | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) Th
3 | Functionality Phase1: | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
| 3.1 Deploy and set up database and application | 13/09/2019 | 17/09/2019 | 2 |  |  |  | 80% | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
3.2 Generate required code : | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) W
| 3.2.1 login function, logout function (including students and admin) | 13/09/2019 | 17/09/2019 | 1 |  |  | ZY, ZC | 90% | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) W
| 3.2.2 bidding function for Round 1 | 13/09/2019 | 17/09/2019 | 4 |  |  | SEB, SJ, MAU | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) W
| 3.2.3 admin-bootstrap function | 13/09/2019 | 17/09/2019 | 5 |  |  | ZY, ZC | 50% | Doesn't include validation | bar: WEEK 4 (9/9 - 15/9) F to WEEK 5 (16/9 - 22/9) W
4 | Test finished function | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
| 4.1 Create Test Case and perform local testing | 2019-09-17 | 2019-09-20 | 2 |  |  | All | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) F
| 4.2 Debugging and regression testing | 2019-09-17 | 2019-09-20 | 4 |  |  | All | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) F
5 | Discussion on new feature | 2019-09-18 | 2019-09-18 | 3 |  |  | All | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
Iteration 2
1 | Review Project Planning and Update work breakdown structure | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2 | Functionality Phase 2 | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.1 Understand Requirements for JSON Checker and modify json_checker.php for JSON APIs | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.2 Develop JSON API interface for Retrieve,Create, Edit and Delete | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3 Modify JSON APIs | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.4 Run test cases for JSON APIs and modify accordingly | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
Milestone | Week 7 PM Review Presentation | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W; WEEK 6 (23/9 - 29/9) F
Iteration 3
1 | Intermediate Planning to react to changes | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
1.1 Review Project Schedule and Update Work Breakdown Structure | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
1.2 Develop Critical Path for Iteration 3 and 4 | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2 | Functionality Phase 3 | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.1 Biding function for Round 2 (real-time) | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.2 Admin-bootstrap function | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.2.1 Start and Clearing Round 1 | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.2.2 Clearing Round 2 | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3 Test Finished Functions | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3.1Test all JSON APIs with bootstrap | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3.2Perform Local Testing and deploy to AWS | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3.3Test on AWS | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.3.4Debugging and regression testing | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
Create Invitations for Meeting | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
Milestone | Week 9 Application Demo and Progress Update | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W; WEEK 9 (14/10 - 20/10) F
Iteration 4
1 | Prepare Power Point Slide for UAT | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2 | Planning to react to chages | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
2.1Review Project Schedule and update breakdown structure | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
3 | Reaction to changes and reviewing | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
3.1 Review php Code | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
3.2 Review JSON Test | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
3.3 Review Bootstrap Test | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W
Milestone | Week 12 User Acceptance Test (UAT) | bar: WEEK 5 (16/9 - 22/9) M to WEEK 5 (16/9 - 22/9) W; WEEK 12 F
Iteration 5
1 | Prepare Power Point Slide for Final Presentation
2 | Making of final edits
2.1 Review php code
2.2 Review JSON TEST
2.3 Review Bootstrap test
Milestone | Week 14 Final Presentation | bar: WEEK 14 F

## Gantt Chart w % Complete
#NAME?
GANTT CHART TEMPLATE |  |  |  | Build better gantt charts with TeamGantt for FREE!
To edit this chart, you must first make a copy. Go to File, the select Make a Copy.
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 3 | 3 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 3 | 2.4 | 0.6 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 5 | 3 | 2 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 5 | 2 | 3 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 6 | 1.2 | 4.8 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 3 | 3 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 7 | 5.6 | 1.4 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 2 | 1.2 | 0.8 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 4 | 1.6 | 2.4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 4 | 4 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 1 | 0.8 | 0.2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 4 | 2.4 | 1.6 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 3 | 1.2 | 1.8 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 3 | 0.6 | 2.4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 9 | 9 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 5 | 4 | 1 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 6 | 3.6 | 2.4 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 1 | 0 | 1 | Rachel | 0%

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%