## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | High | 5 | 8 | Use the planned debugging time in the iteration.
2 | 1 | Login (User) | Login page has undefined variable 'error' | Low | 1 |  | Fixed
3 | 1 | Login (User) | Login page displayed error message "A session had already been started" | Low | 1
4 | 1 | Biding | Biding page displayed syntax error, unexpected '}' | Low | 1
5 | 2 | Admin(Bootstrap) | When importing SamplateData(3) zip file to validate section.csv, actual result was correct but it gave warning of ' Undefined variable:field in include/bootstrap.php on line 254' | Low | 1 | 42 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
6 | 2 | Admin(Bootstrap) | When importing a zip file with missing student.csv, actual result was correct but it gave warning of 'invalid argument supplied for foreach() in processBootstrap.php o line89' . | Low | 1
7 | 2 | Admin(Bootstrap) | When importing SamplateData(1) zip file to validate student.csv, actual result was correct but it gave warning of 'Trying to get property edollar of 'non-object' in include/BidDAO.php on line 107' | Low | 1
8 | 2 | Admin(Bootstrap) | Unable to validate exam start and end time in course.csv (exam start time later than end time) | High | 5
9 | 2 | Admin(Bootstrap) | Unable to validate userid with different casing in course_completed.csv | High | 5
10 | 2 | Admin(Bootstrap) | Unable to display error messages when importing SampleData(6 and 7).zip to validate bid.csv | Low | 1
11 | 2 | Bidding (add bid) | Unable to update bid amount when student bid twice for same section in the same round | High | 5
12 | 2 | Bidding (add bid) | Unable to validate if student has not completed the prerequisite | High | 5
13 | 2 | Bidding(add bid) | When validating if student can add a bid with an incorrect course code, page displayed notice of 'Trying to get property 'school' of non-object'. | Low | 1
14 | 2 | Bidding(drop bid) | Unable to drop a bid with correct course code and section number | High | 5
15 | 2 | Round 1 solution | After importing r1_solution_test_2 zip file to validate round1 clearing of 2bids at the clearing price, actual result was correct but page displayed 10 bids succeed | Low | 1
16 | 2 | Round 1 solution | After importing r1_solution_test_4 zip file to validate round1 clearing of 11bids at the clearing price, actual result was correct but page displayed 10 succeed bids | Low | 1
17 | 2 | AWS(deployment) | file name case-sensitive issue | Critical | 10
18 | 3 | Admin(Bootstrap) | After click the button to import SampleData_lter3.zip file. There is a error of array to string conversion | High | 5 | 16 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
19 | 3 | Bidding(add bid) | Uncoonsistent of the bidding status. If a student bid less than the min amount of the current bid, then the bid sould be unsuccessful. But the message is bid added succcessfully with the status of unsuccessful | Low | 1
20 | 3 | Bidding (add bid) | Unable to validate if a student has already bidded for five course | High | 5
21 | 3 | Bidding(add bid) | Unable to validate that in round 2 the next person bid must place more amount than the smallest one | High | 5
22 | 3 | Bidding( add bid) | Unable to drop bid or drop section for the successful bid | High | 5 |  | Use the planned debugging time in the iteration.
23 | 4 | json stop | Clearing logic not added in | Low | 1 | 19 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
24 | 4 | authenticate | Case sensitivity for username not working for json, but working for manual | Low | 1
25 | 4 | section-dump | php error because it's doing foreach() for empty array when section-dump during R1 | Low | 1
26 | 4 | section-dump | php error when validating incorrect section | Low | 1
27 | 4 | section-dump | it's dumping every bid regardless of course/section during inactive round | High | 5
28 | 4 | update-bid | class/exam timetable clash did not account for clashes with course enrolled in R2 | Low | 1
29 | 4 | section-dump | After round 2 ended, it returned all enrolled students who bidded in round 1 & 2 | Low | 1
30 | 4 | bid-dump | Bids were not sorted by userid when same amount | Low | 1
31 | 4 | bootstrap(JSON) | Not all error messages were sorted in alphabetical order but returned correct error messages | Low | 1
32 | 4 | dump | Bids were sorted from highest bid to lowest bid instead of course | Low | 1
33 | 4 | database | edollar is not stored as 2d.p. | High | 5
34 | 5 | Bidding(add bid in round 2) | edollar is not displayed in correct format e.g $23.90 | Low | 1 | 30 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
35 | 5 | Bidding(add bid in round 2) | Unable to validate if user has already bidded for five course in round 2 | High | 5
36 | 5 | Class Timetable | Unable to display all the courses in the class timetable if the user had 5 modules | Low | 1
37 | 5 | bid-status | Bids were not sorted in the reverse order by the bid amount after round 2 ended | Low | 1
38 | 5 | bid-status | Unable to validate invalid section | High | 5
39 | 5 | bid-status | Unable to get all the bids incluing successful and fail bids after round 1 ended | Low | 1
40 | 5 | dump | Bids in section-student were not sorted in the order of course code | Low | 1
41 | 5 | dump | After round 1 ended, result for the section-student table included the fail bids | High | 5
42 | 5 | AWS | when trying to drop a bid, it displayed "drop-bid file was not found" | Critical | 10

## Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | Resolved | 2019-09-24 | 2019-09-30 | MLJX+ SHKX
2 | 1 | Login (User) | Login page has undefined variable 'error' | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
3 | 1 | Login (User) | Login page displayed error message "A session had already been started" | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
4 | 1 | Biding | Biding page displayed syntax error, unexpected '}' | Resolved | 2019-09-24 | 2019-09-24 | MLJX+ SHKX
5 | 2 | Admin(Bootstrap) | When importing SamplateData(3) zip file to validate section.csv, actual result was correct but it gave warning of ' Undefined variable:field in include/bootstrap.php on line 254' | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
6 | 2 | Admin(Bootstrap) | When importing a zip file with missing student.csv, actual result was correct but it gave warning of 'invalid argument supplied for foreach() in processBootstrap.php o line89' . | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
7 | 2 | Admin(Bootstrap) | When importing SamplateData(1) zip file to validate student.csv, actual result was correct but it gave warning of 'Trying to get property edollar of 'non-object' in include/BidDAO.php on line 107' | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
8 | 2 | Admin(Bootstrap) | Unable to validate exam start and end time in course.csv (exam start time later than end time) | Resolved | 2019-09-29 | 2019-10-05 | CZY+ SHKX
9 | 2 | Admin(Bootstrap) | Unable to validate userid with different casing in course_completed.csv | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
10 | 2 | Admin(Bootstrap) | Unable to display error messages when importing SampleData(6 and 7).zip to validate bid.csv | Resolved | 2019-09-29 | 2019-10-02 | CZY+ SHKX
11 | 2 | Bidding (add bid) | Unable to update bid amount when student bid twice for same section in the same round | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
12 | 2 | Bidding (add bid) | Unable to validate if student has not completed the prerequisite | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
13 | 2 | Bidding(add bid) | When validating if student can add a bid with an incorrect course code, page displayed notice of 'Trying to get property 'school' of non-object'. | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
14 | 2 | Bidding(drop bid) | Unable to drop a bid with correct course code and section number | Resolved | 2019-10-01 | 2019-10-02 | MLJX + SZC
15 | 2 | Round 1 solution | After importing r1_solution_test_2 zip file to validate round1 clearing of 2bids at the clearing price, actual result was correct but page displayed 10 bids succeed | Resolved | 2019-10-05 | 2019-10-05 | CZY+ SHKX
16 | 2 | Round 1 solution | After importing r1_solution_test_4 zip file to validate round1 clearing of 11bids at the clearing price, actual result was correct but page displayed 10 succeed bids | Resolved | 2019-10-05 | 2019-10-05 | CZY+ SHKX
17 | 2 | AWS(deployment) | file name case-sensitive issue | Resolved | 2019-10-15 | 2019-10-16 | CZY+ SHKX
18 | 3 | Admin(Bootstrap) | After click the button to import SampleData_lter3.zip file. There is a error of array to string conversion | Resolved | 2019-10-16 | 2019-10-16 | CSJ+ SHKX
19 | 3 | Bidding(add bid) | Uncoonsistent of the bidding status. If a student bid less than the min amount of the current bid, then the bid sould be unsuccessful. But the message is bid added succcessfully with the status of unsuccessful | Resolved | 2019-10-16 | 2019-10-16 | CZY+ MLJX
20 | 3 | Bidding (add bid) | Unable to validate if a student has already bidded for five course | Resolved | 2019-10-16 | 2019-10-16 | CSJ+ MLJX
21 | 3 | Bidding(add bid) | Unable to validate that in round 2 the next person bid must place more amount than the smallest one | Resolved | 2019-10-16 | 2019-10-16 | CSJ+ MLJX
22 | 3 | Bidding( add bid) | Unable to drop bid or drop section for the successful bid | Resolved | 2019-10-25 | 2019-10-27 | CZY + SJ
23 | 4 | json stop | Clearing logic not added in | Resolved | 2019-10-25 | 2019-10-29 | CZY + SJ
24 | 4 | authenticate | Case sensitivity for username not working for json, but working for manual | Resolved | 2019-10-25 | 2019-10-29 | CZY + SJ
25 | 4 | section-dump | php error because it's doing foreach() for empty array when section-dump during R1 | Resolved | 2019-10-25 | 2019-10-29 | CZY + SJ
26 | 4 | section-dump | php error when validating incorrect section | Resolved | 2019-10-25 | 2019-10-29 | CZY + SJ
27 | 4 | section-dump | it's dumping every bid regardless of course/section during inactive round | Resolved | 2019-10-25 | 2019-10-29 | CZY + SJ
28 | 4 | update-bid | class/exam timetable clash did not account for clashes with course enrolled in R2 | Resolved | 2019-10-30 | 2019-10-30 | CZY + MLJX
29 | 4 | section-dump | After round 2 ended, it returned all enrolled students who bidded in round 1 & 2 | Resolved | 2019-10-30 | 2019-10-30 | CZY + MLJX
30 | 4 | bid-dump | Bids were not sorted by userid when same amount | Resolved | 2019-10-30 | 2019-10-30 | CZY + MLJX
31 | 4 | bootstrap(JSON) | Not all error messages were sorted in alphabetical order but returned correct error messages | Resolved | 2019-10-30 | 2019-10-30 | CSJ + SZC
32 | 4 | dump | Bids were sorted from highest bid to lowest bid instead of course | Resolved | 2019-10-30 | 2019-10-30 | CSJ + SZC
33 | 4 | database | edollar is not stored as 2d.p. | Resolved | 2019-10-31 | 2019-10-31 | CZY + MLJX
34 | 5 | Bidding(add bid in round 2) | edollar is not displayed in correct format e.g $23.90 | Resolved | 2019-11-12 | 2019-11-13 | CZY + MLJX
35 | 5 | Bidding(add bid in round 2) | Unable to validate if user has already bidded for five course in round 2 | Resolved | 2019-11-14 | 2019-11-15 | CZY + MLJX
36 | 5 | Class Timetable | Unable to display all the courses in the class timetable if the user had 5 modules | Resolved | 2019-11-14 | 2019-11-15 | CZY + MLJX
37 | 5 | bid-status | Bids were not sorted in the reverse order by the bid amount after round 2 ended | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC
38 | 5 | bid-status | Unable to validate invalid section | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC
39 | 5 | bid-status | Unable to get all the bids incluing successful and fail bids after round 1 ended | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC
40 | 5 | dump | Bids in section-student were not sorted in the order of course code | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC
41 | 5 | dump | After round 1 ended, result for the section-student table included the fail bids | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC
42 | 5 | AWS | when trying to drop a bid, it displayed "drop-bid file was not found" | Resolved | 2019-11-14 | 2019-11-15 | CSJ + SZC