## Week 13
Person | Question | Week 13: 11 November 2019 to 17 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test
| What will you do today? | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test
| What will you work on today? | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test
| What will you work on today? | Not a working day | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Work on page protection, exam timetable & bidding overview by round number with Zican | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test
| What will you work on today? | Work on page protection, exam timetable & bidding overview by round number with Zican | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Not a working day | Work on page protection, exam timetable & bidding overview by round number with Zican | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test
| What will you work on today? | Work on page protection, exam timetable & bidding overview by round number with Zican | Group meeting to debug UAT, code review | Not a working day | Not a working day | Group meeting to debug json output & AWS test | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week 12
Person | Question | Week 12: 4 November 2019 to 10 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Not a working day | Not a working day | Added radio button for dropping sections with Maurice | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day
| What will you do today? | Not a working day | Not a working day | Not a working day | Added radio button for dropping sections with Maurice | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Not a working day | Not a working day | Added radio button for dropping sections with Zheng Yang | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day
| What will you work on today? | Not a working day | Not a working day | Not a working day | Added radio button for dropping sections with Zheng Yang | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Touch up on UI with Zican | Not a working day | Touch up UI with Sujuan | Not a working day | Finish up r2 bidding, drop bid and drop section UI page with Sujuan | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day
| What will you work on today? | Not a working day | Touch up UI with Sujuan | Not a working day | Finish up r2 bidding, drop bid and drop section UI page with Sujuan | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Not a working day | Touch up UI with Sebastian | Not a working day | Finish up r2 bidding, drop bid and drop section UI page with Sebastian | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day
| What will you work on today? | Not a working day | Touch up UI with Sebastian | Not a working day | Finish up r2 bidding, drop bid and drop section UI page with Sebastian | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Touch up on UI with Sebastian | Not a working day | Not a working day | Not a working day | Not a working day | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day
| What will you work on today? | Not a working day | Not a working day | Not a working day | Not a working day | Group meeting for testing new UI, UAT bug fixing & JSON bid status | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week 11
Person | Question | Week 11: 28 October 2019 to 3 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day
| What will you do today? | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Update test cases for bid-dump | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day
| What will you work on today? | Update test cases for bid-dump | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Not a working day | UAT | Not a working day
| What will you work on today? | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Not a working day | UAT | Not a working day | Touch up on UI with Zican
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day
| What will you work on today? | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Debugging for UAT | UAT | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Not a working day | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Not a working day | UAT | Not a working day
| What will you work on today? | Not a working day | Group meeting to preprare for UAT, final debugging before deployment | Not a working day | Not a working day | UAT | Not a working day | Touch up on UI with Zican
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week 10
Person | Question | Week 10: 21 September 2019 to 28 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | R2 Bid Results | Not a working day
| What will you do today? | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | R2 Bid Results | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | Check through all the dumps apis and feedback to pairs | Update test cases for authenticate and invalid errors
| What will you work on today? | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | Check through all the dumps apis and feedback to pairs | Update test cases for authenticate and invalid errors | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Created course json dump function for student.php, section.php, course.php and updated dump.php | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Updated bid-dump and and section-dump with Zican | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Updated bid-dump and and section-dump with Zican | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Not a working day | Not a working day | R2 Bid Results | R2 Bid Results | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Not a working day | Created course json dump function for student.php, section.php, course.php and updated dump.php | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Updated bid-dump and and section-dump with Sebastian | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Team meeting to discuss the new bid status functionality and assign task for Iteration 4. Brief on the testcases sheet and discuss how to streamline the JSON testing process. Check PP progress and if any issues faced. | Updated bid-dump and and section-dump with Sebastian | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week9
Person | Question | Week 7: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Added delete-bid json api, added update-bid json api, added R1 Add Bid JSON testcases, added start round 1 control onto admin home page, fixed issue with processbootstrap | prepare for the online demo | prepare for the online demo | online demo in class | Not a working day
| What will you do today? | Not a working day | Team meeting to review last week work and prepare for week 9 online demo | prepare for the online demo | Not a working day | online demo in class | Not a working day | Not a working day
| Do you have any obstacles? | No Issues | No Issues | No Issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Added delete-bid json api, added update-bid json api, added R1 Add Bid JSON testcases, added start round 1 control onto admin home page, fixed issue with processbootstrap | prepare for the online demo | prepare for the online demo | online demo in class | Not a working day
| What will you work on today? | Not a working day | Team meeting to review last week work and prepare for week 9 online demo | prepare for the online demo | Not a working day | online demo in class | Not a working day | Not a working day
| Do you have any obstacles? | No Issues | No Issues | No Issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Not a working day | Team meeting to review last week work and prepare for week 9 online demo. Added r2bidding.php, r2BidDAO.php and modified dropsecton.php | prepare for the online demo | prepare for the online demo | online demo in class | Not a working day
| What will you work on today? | Not a working day | Team meeting to review last week work and prepare for week 9 online demo | prepare for the online demo | Not a working day | online demo in class | Not a working day | Not a working day
| Do you have any obstacles? | No Issues | No Issues | No Issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Not a working day | Team meeting to review last week work and prepare for week 9 online demo. Added r2bidding.php, r2BidDAO.php and modified dropsecton.php | prepare for the online demo | prepare for the online demo | online demo in class | Not a working day
| What will you work on today? | Not a working day | Team meeting to review last week work and prepare for week 9 online demo | prepare for the online demo | Not a working day | online demo in class | Not a working day | Not a working day
| Do you have any obstacles? | No Issues | No Issues | No Issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Creating Round 2 Add Bid, Drop Bid and Resolution Testcases | Continue creating Round 2 Add Bid, Drop Bid and Resolution Testcases | Team meeting to review last week work and prepare for week 9 online demo. Finishing the testcase for round 2 bidding | prepare for the online demo | prepare for the online demo | online demo in class | Not a working day
| What will you work on today? | Continue creating Round 2 Add Bid, Drop Bid and Resolution Testcases | Team meeting to review last week work and prepare for week 9 online demo | prepare for the online demo | Prepare testcases and data for online demo | online demo in class | Not a working day | Do the regression testing
| Do you have any obstacles? | No Issues | No Issues | No Issues | No issues | No issues | No issues | No issues

## Week 8
Person | Question | Week 7: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | Not a working day | Not a working day | Coding Round Controls for Admin with validation (UI side). Fixed bugs of data validation for class timetable and round 2 clearing function | Not a working day | Coding round control into bootstrap | Seperated UI/JSON add bid and bootstrap add bid into 2 methods
| What will you do today? | Not a working day | Not a working day | team meeting to review iteration 2, update schedule. Assign tasks for iteration 3 | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issue | No issues | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Not a working day | Coding Round Controls for Admin with validation (UI side). Fixed bugs of data validation for class timetable and round 2 clearing function | Not a working day | Coding round control into bootstrap | Seperated UI/JSON add bid and bootstrap add bid into 2 methods
| What will you work on today? | Not a working day | Not a working day | team meeting to review iteration 2, update schedule. Assign tasks for iteration 3 | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issue | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Not a working day | added basecode for admin token | finished admin token validation and authentication | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Coding JSON Web Token, Validation and Authentication; | team meeting to review iteration 2, update schedule. Assign tasks for iteration 3 | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issue | No issue | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Not a working day | added basecode for admin token | finished admin token validation and authentication | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Coding JSON Web Token, Validation and Authentication; | team meeting to review iteration 2, update schedule. Assign tasks for iteration 3 | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | No issue | No issue | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Not a working day | Not a working day | Not a working day | prepare slides for week 9 online demo | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Not a working day | team meeting to review iteration 2, update schedule. Assign tasks for iteration 3 | Not a working day | Not a working day | Not a working day | Creating Round 2 Add Bid, Drop Bid and Resolution Testcases
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week 7
Person | Question | Week 7: 30 September 2019 to 6 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Not a working day | added dropSection.php page added retrieveByUserid, retrieveByUseridCourse, delete functions changed alignment formatting and UI added CSS for frontend pages, login.php now retains userid after wrong login | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug | Fixed bug with bootstrap data validation, course validation, case insensitive username, and for bootstrap | Not a working day | PM Review, Create test cases for Round 1 resolution | Not a working day
| What will you do today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code | Not a working day | PM Review | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | added Validation for drop bid, validation test code for R2 add bid Reorder retrieve and add and Changed DropBid layout | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug | Fixed bugs with bidding data validation | Not a working day | PM Review | Not a working day
| What will you work on today? | Drop Bid validation, polish up the bidding pages, create Round objects with Zican | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code | Not a working day | PM Review | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | added dropSection.php page added retrieveByUserid, retrieveByUseridCourse, delete functions changed alignment formatting and UI added CSS for frontend pages, login.php now retains userid after wrong login | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug | Fixed bug with bootstrap data validation, course validation, case insensitive username, and for bootstrap | Not a working day | PM Review | Not a working day
| What will you work on today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code | Not a working day | PM Review | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Not a working day | Tested bidding for round 1 and updated bug metrics | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug | Finished the PM power point slides and update bm | Not a working day | PM Review | Not a working day
| What will you work on today? | Not a working day | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code | Not a working day | PM Review | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | no issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Not a working day | added Validation for drop bid, validation test code for R2 add bid Reorder retrieve and add and Changed DropBid layout | Team meeting to review all documents, code, bugs, and presentation for PM Review. AWS deployment and testing and debug | Fixed bugs with bidding data validation | Not a working day | PM Review | Not a working day
| What will you work on today? | Drop Bid validation, polish up the bidding pages, create Round objects with Maurice | Team meeting to review all documents, code, bugs, and presentation for PM Review | Debugging and regression testing for iter 2 code | Not a working day | PM Review | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues

## Week 6
| Question | Week 6: 23 September 2019 to 29 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Create testcase for login, add bid and bootstrap | Not a working day | Planned logic for round 1 clearing | Not a working day | Coded round 1 validation logic | Coded round 1 result page and debugging | Not a working day
| What will you do today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Code round 1 result page and debugging | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No Issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Not a working day | Discussed round 1 clearing logic with team | Not a working day | Not a working day | Add bid validation with Zican | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Add bid validation with Zican | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Not a working day | Fix authentication bug for admin | authentication for admin, home & bootstrap page for admin Planned logic for round 1 clearing | Not a working day | Coded round 1 validation logic | Fixed bugs on login page and created Web UI page for round 1 clearing and round 1 result display | Not a working day
| What will you work on today? | Fix authentication bug for admin | authentication for admin, home & bootstrap page for admin Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Code round 1 result page and debugging | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Sujuan | What did you do yesterday? | Create Drop Bid function and update bidding functionality | NA | Discussion of round 1 clearing logic and tested bootstrap and login with test cases | Not a working day | Update testcases and documentation for login and bidding function | Create testcases for round 1 bidding and resolution | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Create testcases for round 1 bidding and resolution, prepare PM review power point slides | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Add data validation for course_completed and create test cases | Not a working day | Not a working day | Not a working day | Not a working day | Add bid validation with Maurice | Not a working day
| What will you work on today? | Not a working day | Meeting to review schedule ,assign planned hours for critical path and assign tasks to pair in iteration 2 | Not a working day | Not a working day | Add bid validation with Maurice | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | no issues | No issues | No issues | No issues | No issues

## Week 5
Person | Question | Week 5: 16 September 2019 to 22 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? | Created remainder of DAO files from what Maurice did on Saturday, added deleteAll and add method to all DAO files for bootstrap. | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with ZiCan) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed bootstrap
| What will you do today? | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with ZiCan) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed bootstrap | Create testcase for login, add bid and bootstrap
| Do you have any obstacles? | No issues | Problem with data validation for course_completed, prerequisite completed validation | No issues | No issues | No issues | No issues | No issues
Maurice | What did you do yesterday? | Not a working day | Round 1 bidding form, session for login, logout with Sebastian | Not a working day | Add new bid, update existing bid functionality with Sujuan | Update and debug existing bid functionality with Sujuan | Not a working day | Add input and logical vaildation for bid section with Sujuan
| What will you work on today? | session for login, logout, added get course by student id. started round 1 bidding form with Sebastian. | Filters for sections to bid with Sujuan | Meeting to discuss schedule Discuss data validation for course_completed and bid table Add new bid, update existing bid functionality with Sujuan | Update and debug existing bid functionality with Sujuan | Not a working day | Add input and logical vaildation for bid section with Sujuan | Not a working day
| Do you have any obstacles? | No issues | Postponed filtering, going to focus on the bidding functionality first. | No issues | No issues | No issues | No issues | No issues
Sebastian | What did you do yesterday? | Added CSS navigation bar to home page | Round 1 bidding form, session for login, logout with Maurice | Round 1 bidding form | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | added load admin sql, admin class & DAO (add, reset passwod). to finish authenticate & test | Not a working day
| What will you work on today? | session for login, logout, added get course by student id. started round 1 bidding form with Maurice. | Round 1 bidding form | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | added load admin sql, admin class & DAO (add, reset passwod). to finish authenticate & test | Not a working day | Not a working day
| Do you have any obstacles? | No issues | No issues | No issues | No issues | To debug and test | No issues | No issues
Sujuan | What did you do yesterday? | Add retrieve by course and section methods. | Not a working day | Not a working day | Add new bid, update existing bid functionality with Maurice | Update and debug existing bid functionality with Maurice | Not a working day | Add input and logical vaildation for bid section
| What will you work on today? | Not a working day | Filters for sections to bid with Maurice | Meeting to discuss schedule Discuss data validation for course_completed and bid table Add new bid, update existing bid functionality with Maurice | Update and debug existing bid functionality with Maurice | Not a working day | Add input and logical vaildation for bid section with Maurice | Not a working day
| Do you have any obstacles? | No issues | Postponed filtering, going to focus on the bidding functionality first. | No Issues | No issues | No issues | No issues | No issues
Zican | What did you do yesterday? | Created Login page with authentication from database | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with Zheng Yang) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed
| What will you work on today? | Plan data validation for bootstrap | Added data validation for student, course, section and prerequisite for bootstrap. (pp with Zheng Yang) | Meeting to discuss schedule Discuss data validation for course_completed and bid table | Not a working day | Not a working day | Add data validation for course_completed | Add data validation for course_completed and create test cases
| Do you have any obstacles? | No issues | Problem with data validation for course_completed, prerequisite completed validation | No issues | No issues | No issues | No issues | No issues

## Week 4
Person | Question | Week 4: 9 September 2019 to 15 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Zheng Yang | What did you do yesterday? |  |  |  |  | NA | Team meeting | Created minutes for meeting
| What will you do today? |  |  |  |  | Team meeting | Created minutes for meeting | Created remainder of DAO files from what Maurice did on Saturday, added deleteAll and add method to all DAO files for bootstrap.
| Do you have any obstacles? |  |  |  |  | No issues | No Issues | No issues
Maurice | What did you do yesterday? |  |  |  |  | NA | Change folder structure on repo to the one on wiki Create barebones class files for the 6 DB tables | Create a couple of basic retrieveAll() methods
| What will you work on today? |  |  |  |  | Change folder structure on repo to the one on wiki Create barebones class files for the 6 DB tables Team meeting | Create a couple of basic retrieveAll() methods | Not a working day
| Do you have any obstacles? |  |  |  |  | Had to make placeholder files to push empty folders to github | NA | NA
Sebastian | What did you do yesterday? |  |  |  |  | NA | Team Meeting | Not a working day
| What will you work on today? |  |  |  |  | Team Meeting | Not a working day | Added CSS navigation bar to home page
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | No issues
Sujuan | What did you do yesterday? |  |  |  |  | NA | NA | NA
| What will you work on today? |  |  |  |  | Team meeting | Not a working day | Add retrieve by course and section methods in the course and section DAO. Create Course_completedDAO
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | NA
Zican | What did you do yesterday? |  |  |  |  | NA | Team meeting | Not a working day
| What will you work on today? |  |  |  |  | Team meeting | Not a working day | Created Login page with authentication from database
| Do you have any obstacles? |  |  |  |  | No Issues | No issues | No Issues