## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | High | 2 | 3 | Use the planned debugging time in the iteration.
2 | 1 | Login (User) | Login page has undefined variable error | Low | 1 |  | Fixed
3 |  |  |  | Low | 0
4 |  |  |  | Low
5 |  |  |  | Low
6 |  |  |  | Critical
7 |  |  |  | Low |  | 0 | Use the planned debugging time in the iteration.
8 |  |  |  | Low
9 |  |  |  | Low
10 |  |  |  | High
11 |  |  |  | Low
12 |  |  |  | Low
13 |  |  |  | Critical
14 |  |  |  | High |  | 0 | Use the planned debugging time in the iteration.
15 |  |  |  | High
16 |  |  |  | High
17 |  |  |  | High
18 |  |  |  | Low |  | 0 | Use the planned debugging time in the iteration.
19 |  |  |  | High
20 |  |  |  | Low
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | Successful login with incorrect username(case insensitive) and correct passowrd | Resolved | 2019-09-24
2 | 1 | Login (User) | Login page has undefined variable error | Resolved | 2019-09-24 | 2019-09-25 | MLJX + SZC
3 | 0 | 0 | 0 | Unresolved
4 | 0 | 0 | 0 | Unresolved
5 | 0 | 0 | 0 | Unresolved
6 | 0 | 0 | 0 | Unresolved
7 | 0 | 0 | 0 | Unresolved
8 | 0 | 0 | 0 | Unresolved
9 | 4 | Bootstrap | 0 | Unresolved
9 | 3 | Heatmap | 0 | Unresolved
10 | 3 | Heatmap | 0 | Unresolved
11 | 3 | Heatmap | 0 | Unresolved
13 | 3 | Heatmap | 0 | Unresolved
14 | 4 | Popular Place | 0 | Unresolved
15 | 4 | Popular Place | 0 | Unresolved
16 | 4 | Popular Place | 0 | Unresolved
17 | 0 | 0 | 0 | Unresolved
18 | 0 | 0 | 0 | Unresolved
19 | 0 | 0 | 0 | Unresolved
20 | 0 | 0 | 0 | Unresolved
21 | 0 | 0 | 0 | Unresolved